## Slide 1
PLATFORM MIGRATION PROPOSAL
SMArT
Dataiku DSS + Snowflake
→ Databricks Apps + Delta Lake
May 2026 · v1.0 · Draft for Review
Business Owners
Dev Team
Management
Digital/Platform
ATP GPD Expl Workspace · Unity Catalog: gpdip_smart_us_east_1 · Confidential

## Slide 2
The Case for Change
86%
Cost Reduction
$30,900 → ~$4,200/yr
$26.7K
Annual Savings
Break-even within year 1
20 wks
Migration Timeline
Existing team, phased delivery
WHY MIGRATE NOW
High Fixed Cost
3 DSS Designer licenses @ $10,300 each — fixed regardless of usage
Platform Dependency
Every deployment needs Platform Support team scheduling
Limited AI Ecosystem
No native LLMs, MLflow, model serving, or vector search
Strategic Misalignment
DSS + Snowflake outside GPDIP platform direction — growing technical debt

## Slide 3
Current → Target Architecture
CURRENT (Dataiku DSS + Snowflake)
Platform
Dataiku DSS
Framework
Python Flask / FastAPI
Database
Snowflake (14 tables, <100 GB)
Deployment
Manual DSS Bundle — Platform Team
Environments
3 physically isolated DSS instances
AI / ML
Not available
→
TARGET (Databricks Apps + Delta Lake)
Platform
Databricks Apps (ATP GPD Expl)
Framework
Python Flask / FastAPI (unchanged)
Database
Delta Lake (Unity Catalog, dedicated)
Deployment
CI/CD (GitHub Actions + DAB, automated)
Environments
3 schemas in one catalog (RBAC isolated)
AI / ML
MLflow · Model Serving · Genie AI ✓

## Slide 4
Cost Analysis & ROI
Chart: 
| Licensing | Compute | Storage | Support
Dataiku DSS (Current) | 30900 | 0 | 0 | 0
Databricks (Proposed — Conservative) | 0 | 5516 | 336 | 0
DATABRICKS BREAKDOWN
Conservative scenario · annual
Prod App compute
24/7, $305/mo
~$3,660/yr
Dev App compute
10h/day, $110/mo
~$1,320/yr
Stage App compute
8h/day, $75/mo
~$900/yr
SQL Warehouses
All envs combined
~$2,880/yr
Delta Lake storage
~70GB avg, $14/mo
~$168/yr
Unity Catalog
Premium tier
Included
TOTAL ~$5,880 / year
💰 Annual Savings: ~$25,020 (81% reduction) · Conservative scenario · Optimised (off-hours + 1yr CUD): ~$4,200/yr (86% saving)

## Slide 5
Deployment Model & ADLC Compliance
CI/CD DEPLOYMENT WORKFLOW
1
develop branch
CI/CD → smart-app-dev
Dev self-testing
2
stage branch
CI/CD → smart-app-stage
QA / UAT (qTest)
3
main branch
CI/CD → smart-app-prod
RFC gate required
ADLC COMPLIANCE SATISFIED
✓
QA vs Prod separation
Schema isolation + UC RBAC
✓
Validation before prod
ServiceNow RFC gates CI/CD
✓
Test evidence
qTest (unchanged)
✓
Change tracking
Jira + RFC + Git history
✓
Prod access control
CI/CD service principal only
✓
Audit trail
UC audit log + CI/CD runs
ServiceNow RFC process fully preserved

## Slide 6
AI Integration Roadmap
1
Phase 1 — Post Migration
Flask/FastAPI unchanged on Databricks Apps
Delta Lake replaces Snowflake
Same user experience
Foundation for all future AI
2
Phase 2 — What-If Analysis
MLflow: scenario comparison & tracking
Databricks Workflows: parallel runs
Mosaic AI: instant enrollment predictions
Unity Catalog Feature Store: shared features
3
Phase 3 — Future Enhancements
Genie AI: natural language data queries
Predictive site activation ML model
LLM-assisted scenario generation
Anomaly detection on simulation inputs
All AI capabilities available at no additional infrastructure cost on Databricks

## Slide 7
Migration Plan — ~17 Weeks
~17 Wks
~4 Months
1
Discovery &
Architecture
1.5–2w
Wks 1–2
Phase 1
Requirements validation
Databricks workspace setup
Unity Catalog & RBAC design
ADLC & security review
2
Environment,
CI/CD & Data
6w
Wks 3–8
Phases 2 + 3
DAB + GitHub Actions setup
Service Principals & RBAC
Dev/Stage/Prod configuration
Snowflake → Delta Lake migration
Schema validation & testing
3
Backend &
Frontend Migration
5w
Wks 5–12
Phases 4 + 5
Flask → Databricks Apps
Config & secrets refactoring
UI validation & API testing
Env-specific configuration
Dev testing & iteration
4
QA, UAT &
Performance
2.5w
Wks 13–15
Phases 6 + 7
Stage deployment
Full QA/UAT (qTest)
ServiceNow RFC raised
Concurrent user testing
Delta query & compute tuning
5
Go-Live &
Hypercare
3w
Wks 15–17
Phases 8 + 9
Runbooks & rollback strategy
RFC approval → prod deploy
DSS & DBX parallel run (2w)
User acceptance & sign-off
DSS decommission
Total ~17 weeks · 9 detailed sub-phases · See Effort Estimation slide for full breakdown
~4 months end-to-end

## Slide 8
We Recommend
Proceed with
the Migration
💰 86% cost saving — $26.7K/yr
🔗 Strategic platform alignment (GPDIP)
⚙ Operational independence via CI/CD
🤖 AI-ready without extra infrastructure
IMMEDIATE NEXT STEPS
1. Confirm workspace with Digital/Platform team
2. Identify migration lead & confirm team availability
3. 1-week PoC: deploy Flask app as Databricks App

## Slide 9
?
CLIENT QUESTIONS — DAN
Responses to
Dan's Queries
Feasibility check completed · Migration app built with live UI, APIs & Delta Lake tables
Q1 — Risks & Cons to consider
Q2 — UI, UX & performance impact
Q3 — Feature work during migration
SMArT Platform Migration · Response to Dan's Review

## Slide 10
Q1
Risks & Cons to Consider
We are transparent about trade-offs. These are manageable risks — none are blockers, and all have defined mitigations.
LOW RISK
Short-term team upskilling
Team needs to learn Databricks Apps, DAB & CI/CD patterns. Mitigated by feasibility spike already completed — team is hands-on from day one.
LOW RISK
No physical environment isolation
Logical schema separation replaces physical DSS instances. UC RBAC enforces access boundaries; reviewed and accepted by compliance approach.
MED RISK
Migration window carries delivery risk
20-week project introduces schedule risk. Phased delivery with parallel-run period and rollback path (DSS stays live until RFC sign-off) contains impact.
LOW RISK
Usage-based cost variability
Unlike fixed DSS licenses, Databricks costs scale with usage. Auto-shutdown on dev/stage and cost dashboards keep this well within the $4.2K estimate.
LOW RISK
Data migration validation effort
14 Snowflake tables must be migrated and verified. Row-count and schema validation scripts are part of Phase 2; feasibility run confirms process works.
MED RISK
Dependency on Digital/Platform team
Workspace assignment (ATP GPD Expl) needs Digital team confirmation. Already flagged as first action item; planning can proceed in parallel under Option A.
✓ Overall assessment: No identified cons are blockers. Risk profile is LOW–MEDIUM. Feasibility PoC de-risks the highest-uncertainty items.

## Slide 11
Q2
UI, End-User Experience & Performance
✅ Feasibility proven: Migration app built with exact UI, live backend APIs & Delta Lake tables — user experience validated end-to-end.
🖥 UI & Frontend
Redesign needed?
None
Identical Flask/FastAPI frontend deployed as Databricks App — same screens, same navigation, same URLs.
Functionality loss?
None
All features confirmed working in the PoC migration. No capability is removed or degraded.
Look & feel change?
None
Databricks App is a thin hosting wrapper — users will not see any platform change.
⚡ Performance
Calculation speed
Same / Faster
Same Python simulation engine. Databricks serverless compute removes DSS scheduler overhead.
Page load times
No change
API layer is unchanged. Delta Lake SQL connector benchmarks comparably to Snowflake at this data volume (<100 GB).
Peak load (50 users)
Handled
Medium instance (2 vCPU / 6 GB) sized for <100 concurrent. Scale-up to Large available on demand.
👤 User Impact
Training required?
None
End users interact with the same web application. No Databricks knowledge needed by users.
URL / access change?
New URL
Each environment gets a dedicated Databricks App URL. A bookmark update is the only visible change for users.
Downtime at cutover?
Zero planned
2-week parallel run means DSS and Databricks run simultaneously. Cutover is a DNS/redirect flip.

## Slide 12
Q3
Feature Work During the Migration
✅ Short answer: Feature work does NOT need to be paused. Migration and new features can run in parallel.
HOW THIS WORKS IN PRACTICE
MIGRATION
TRACK
Foundation
Wks 1–4
Data
Wks 5–8
App Migration
Wks 5–12
QA / UAT
Wks 13–16
Go-Live
Wks 17–20
FEATURE
TRACK
Bug fixes &
maintenance
New Feature A
(on DSS)
New Feature B
(on DSS)
Feature C → DBX
(new home)
Cutover
THE GUARDRAILS
1
New features built on DSS as normal
During migration, feature development continues on the current DSS platform. No change to today's dev/QA/release workflow for new features.
2
Migration team is a dedicated workstream
Migration is run as a parallel project track — it does not consume the full team. Feature sprints and migration sprints are planned independently.
3
Features completed before cutover ship on DSS; after cutover on Databricks
Any feature in flight at Go-Live week is evaluated: if complete → ship on DSS, if not → brief hold during 2-week parallel run, then deliver on Databricks.

## Slide 13
✦
Genie AI — Natural Language Querying for SMArT
Users ask plain-English questions against SMArT's Delta Lake tables — no SQL, no dashboards. Three implementation paths, increasing in capability.
1
✅ READY NOW
Genie Space
Standalone — zero code changes
Create a Genie Space in Databricks pointing to smart_poc.smart.* Delta tables. Users ask questions directly in the Databricks workspace UI.
EXAMPLE QUESTIONS
💬 "Which country has the highest P90 days?"
💬 "Show activation timelines for Argentina"
💬 "Avg site activation rate across countries?"
⚡ Separate UI — users leave the SMArT app
2
⚠ REQUIRES WORK
Embed Genie in App
Chat widget inside SMArT webapp
Add a chat widget in the React frontend. Flask backend proxies calls to the Genie Conversation API. Results rendered inline in the app.
EXAMPLE QUESTIONS
💬 Genie Conversation API
💬 Flask → Genie API proxy
💬 SQL results inline in app UI
⚡ Cannot answer questions about live in-memory API results
3
🔄 BEST OF BOTH
Write Results → Genie Queries
Most powerful approach
Analysis results are saved back to Delta tables (site_activation_details_results etc.). Genie queries saved results — combines live app + historical analysis.
EXAMPLE QUESTIONS
💬 "Show all plans created this week"
💬 "Compare P90 dates across my last 3 runs"
💬 "Which analysis had the fastest activation?"
⚡ Requires result-persistence logic in app layer

## Slide 14
✦
Genie — Recommended Path & Architecture
★ RECOMMENDED FOR PoC DEMO — OPTION 1
1
Open ATP GPD Expl workspace → Genie (sidebar)
2
Create a Genie Space → connect to smart_poc.smart.*
3
Point at smart_category_activation_timelines table
4
Demo alongside app — zero code changes required
✓ CAN answer
✓ Questions about Delta Lake tables
✓ Raw data, saved plans, timelines
✓ Historical result comparisons (Opt 3)
✗ CANNOT answer
✗ Live API/in-memory computation results
✗ Runtime simulation state
✗ Unless Option 3 (write back) is implemented
OPTION 3 — TARGET ARCHITECTURE (Best of Both)
SMArT Web App
React + Flask/FastAPI
Flask Backend
Proxy → Genie Conversation API
Delta Lake Tables
smart_poc.smart.* + results tables
Genie Space
Natural language → SQL → Delta Lake
Result write-back:
site_activation_details_results · summary_results → queryable by Genie

## Slide 15
$
DETAILED COST ANALYSIS
Databricks Pricing
& Cost Strategies
AWS Premium Tier · All 3 Environments · Pay-as-you-go → Committed pricing
Per-environment breakdown
3 cost scenarios
Optimization strategies
Current stack comparison
SMArT Platform Migration · June 2026

## Slide 16
DBU Rates & Per-Environment Cost Breakdown
DBU RATES — AWS Premium Tier
Databricks App (Medium)
$0.275/hr
SQL Serverless Warehouse
$1.10/hr active
1-yr commit discount
25–45% saving
3-yr commit discount
40–55% saving
🛠 DEV
App (10 hrs/day × 22 days)
$60–$80
SQL Warehouse (~2 hrs/day)
$48–$60
Delta Lake Storage (~10 GB)
$2–$5
Unity Catalog
Included
TOTAL ~$110–$145/mo
🧪 STAGE
App (8 hrs/day × 22 days)
$48–$65
SQL Warehouse (~1 hr/day)
$24–$30
Delta Lake Storage (~10 GB)
$2–$5
Unity Catalog
Included
TOTAL ~$75–$100/mo
🚀 PROD
App (24/7 always-on)
$200–$270
SQL Warehouse (~4 hrs/day)
$96–$120
Delta Lake Storage (50–100 GB)
$10–$25
Unity Catalog
Included
TOTAL ~$305–$415/mo
ℹ App size: Medium (0.5 DBU/hr) · DBU rate: $0.55 pay-as-you-go · Region: AWS us-east-1 · Unity Catalog included at Premium tier

## Slide 18
Cost Optimization Strategies
1
40–60% on Dev/Stage
Stop Dev/Stage outside business hours
Auto-shutdown after 30-min idle. Dev/Stage only run ~10 hrs/day instead of 24/7. Biggest single lever for non-prod environments.
2
25–45% across all envs
Committed DBU pricing (1yr or 3yr)
1-year commit: ~$0.40–0.50/DBU vs $0.55 pay-as-you-go. 3-year commit: ~$0.30–0.40/DBU. Significant reduction once usage is proven stable.
3
50% on App compute
Small app size instead of Medium
Downsize from Medium (0.5 DBU/hr) to Small (0.25 DBU/hr) for Dev/Stage. Halves App compute cost if performance is sufficient for non-prod workloads.
4
Pay only for queries
Serverless SQL auto-suspend
Default Serverless Warehouse behaviour — billing stops immediately when idle. No minimum charge. Combine with query result caching to reduce active hours.
5
Reduce workspace overhead
Dev/Stage share a single workspace
Schema-based isolation within one workspace eliminates duplicate workspace overhead. Unity Catalog RBAC enforces access control between schemas.
Optimised (off-hours + 1yr commit): ~$350/mo (~$4,200/yr) | Off-hours + 3yr commit: ~$280/mo (~$3,360/yr)

## Slide 19
Stack Comparison: Current vs Databricks
CURRENT — Dataiku + Snowflake
PROPOSED — Databricks
Platform License
Dataiku license (significant fixed cost)
→
Included in DBU consumption
Compute Model
Dataiku infrastructure (fixed)
→
Serverless — pay-per-use only
Database Cost
Snowflake — separate license + compute
→
Delta Lake — S3 storage at $0.023/GB/mo
App Hosting
Dataiku webapp
→
Databricks Apps (0.5 DBU/hr)
Data Governance
Manual / limited
→
Unity Catalog — included with Premium
CI/CD
Custom setup required
→
Databricks Asset Bundles (DABs) native
Dev/Stage Cost
Fixed (same as prod license cost)
→
Usage-based — auto-shutdown saves 40–60%
Annual Total (est.)
$30,900/yr
→
$4,200–$5,880/yr (optimised–conservative)

## Slide 20
Recommended Cost Strategy & Savings Roadmap
Day 1
Go-Live
Pay-as-you-go
+ Auto-shutdown
~$350/mo
~$4,200/yr
86% vs DSS
Medium app (0.5 DBU/hr) all envs
Dev/Stage off-hours auto-shutdown
Serverless SQL, no idle cost
Unity Catalog included
Year 1
Review
1-Year
Commit (CUD)
~$230/mo
~$2,760/yr
91% vs DSS
Apply 1yr commit after usage proven
Rate drops to ~$0.40–0.50/DBU
Review app sizing (Small vs Medium)
~25–45% further reduction
Year 2+
Optimised
Small App Size
+ 1yr CUD
~$180/mo
~$2,160/yr
93% vs DSS
Downsize Dev/Stage to Small (0.25 DBU)
Prod stays Medium if load requires
Further 50% App compute reduction
Dev/Stage share single workspace
Year 3+
Full Optimised
3-Year
Commit (CUD)
~$140/mo
~$1,680/yr
95% vs DSS
3yr commit: ~$0.30–0.40/DBU
Lowest possible unit cost
Full AI stack (Genie, MLflow) included
Cost well below any alternative

## Slide 21
Migration Effort Estimation — 9 Phases
~17 Weeks
Total
#
Phase
Key Activities
Effort
Weeks →
0
1
2
3
4
1
Discovery & Architecture
Requirements validation · Databricks workspace setup · Unity Catalog design · ADLC & security review
1.5–2 wks
1.5–2 wks
2
Environment & CI/CD Setup
DAB setup · GitHub Actions · Service Principals · RBAC · Dev/Stage/Prod configuration
3 wks
3 wks
3
Data Migration
Snowflake schema analysis · Delta Lake design · migration scripts · validation testing
3 wks
3 wks
4
Backend Migration
Flask adaptation for Databricks Apps · configuration refactoring · secrets management
4 wks
4 wks
5
Frontend & Integration Testing
UI validation · API testing · environment-specific configuration
1 wk
1 wk
6
QA & UAT Deployment
Stage deployment · defect fixing · performance testing
1 wk
1 wk
7
Performance & Load Testing
Concurrent user testing · Delta query tuning · compute optimization
0.5 wk
8
Production Deployment Prep
Runbooks · rollback strategy · production readiness review
1 wk
1 wk
9
Parallel Run & Hypercare
DSS & Databricks side-by-side validation · user acceptance · bug fixes
2 wks
2 wks
TOTAL ESTIMATED EFFORT
~17 Weeks (including 0.5–1 week buffer for risk and ADLC sign-off)
~4 months end-to-end

## Slide 22
Effort by Phase — Visual Timeline
~17 Weeks
Total
1
Discovery &
Architecture
1.5–2w
2
Environment
& CI/CD
3w
3
Data
Migration
3w
4
Backend
Migration
4w
5
Frontend &
Integration
1w
6
QA & UAT
Deployment
1w
7
Perf &
Load Test
0.5w
8
Prod Prep
1w
9
Parallel Run
& Hypercare
2w
Critical Path (Backend 4w)
Infrastructure (Env+CI/CD 3w)
Data (Migration 3w)
Validation (QA+Parallel 3w)
Other phases (4w)

## Slide 23
Thank You
SMArT Platform Migration Proposal
Dataiku DSS + Snowflake → Databricks Apps + Delta Lake
📋 Questions — raise with the team
📅 Next: Confirm workspace with Digital/Platform
🚀 Target: 1-week PoC proof of concept
Prepared by the SMArT Engineering Team · May 2026 · Confidential

## Slide 24
Project Plan — SMArT Migration (15 Jun → 28 Sept 2026)
▶ Start
15 Jun 2026
✓ End
28 Sept 2026
June 2026
July 2026
August 2026
September 2026
October 2026
W3
W4
W1
W2
W3
W4
W1
W2
W3
W4
W1
W2
W3
W4
W1
W2
W3
1
Discovery & Architecture
2w
2
Environment, CI/CD & Infra
3w
Environment, CI/CD & Infra
3
Data Migration
⚡parallel
3w
Data Migration
4
Backend Migration
⚡parallel
4w
Backend Migration
5
Frontend & Integration
6
QA, UAT & Perf Testing
2w
7
Prod Prep & Go-Live
8
Parallel Run & Hypercare
2w
Parallel
execution
Start: 15 Jun 2026 · 3 Resources (Tech Lead, Backend Dev, Data Eng) · Completion: 28 Sept 2026 · ⚡ Phases 3 & 4 parallel — saves ~3 weeks
1w

## Slide 25
Resource Allocation & Phase Schedule
Done by
28 Sept 2026
⚡ Key parallelism: Phases 3 (Data Migration) and 4 (Backend Migration) run simultaneously — Data Eng on Delta Lake while Tech Lead + Backend Dev work on Flask. Saves ~3 weeks vs sequential.
Phase
Start
End
Duration
Tech Lead
Backend Dev
Data Eng
Parallel?
Discovery & Architecture
15 Jun
26 Jun
2w
✓
✓
✓
—
Environment, CI/CD & Infra
29 Jun
17 Jul
3w
✓
✓
✓
—
Data Migration (Snowflake→Delta)
20 Jul
07 Aug
3w
–
–
✓
⚡ YES
Backend Migration
20 Jul
14 Aug
4w
✓
✓
–
⚡ YES
Frontend & Integration
17 Aug
21 Aug
1w
✓
✓
✓
—
QA, UAT & Perf Testing
24 Aug
04 Sept
2w
✓
✓
✓
—
Prod Prep & Go-Live
07 Sept
11 Sept
1w
✓
✓
✓
—
Parallel Run & Hypercare
14 Sept
25 Sept
2w
✓
✓
✓
—
Project Start
15 Jun 2026
Project End
28 Sept 2026
Total Duration
~17 weeks
Team Size
3 resources
Parallel Saving
~3 weeks saved