## Slide 1
PLATFORM MIGRATION PROPOSAL
SMArT
Dataiku DSS + Snowflake
→ Databricks Apps + Delta Lake
May 2026 · v1.0 · Draft for Review
Business Owners
Dev Team
Management
Digital/Platform
ATP GPD Expl Workspace · Unity Catalog: gpdip_smart_us_east_1 · Confidential

## Slide 2
The Case for Change
86%
Cost Reduction
$30,900 → ~$4,200/yr
$26.7K
Annual Savings
Break-even within year 1
20 wks
Migration Timeline
Existing team, phased delivery
WHY MIGRATE NOW
High Fixed Cost
3 DSS Designer licenses @ $10,300 each — fixed regardless of usage
Platform Dependency
Every deployment needs Platform Support team scheduling
Limited AI Ecosystem
No native LLMs, MLflow, model serving, or vector search
Strategic Misalignment
DSS + Snowflake outside GPDIP platform direction — growing technical debt

## Slide 3
Current → Target Architecture
CURRENT (Dataiku DSS + Snowflake)
Platform
Dataiku DSS
Framework
Python Flask / FastAPI
Database
Snowflake (14 tables, <100 GB)
Deployment
Manual DSS Bundle — Platform Team
Environments
3 physically isolated DSS instances
AI / ML
Not available
→
TARGET (Databricks Apps + Delta Lake)
Platform
Databricks Apps (ATP GPD Expl)
Framework
Python Flask / FastAPI (unchanged)
Database
Delta Lake (Unity Catalog, dedicated)
Deployment
CI/CD (GitHub Actions + DAB, automated)
Environments
3 schemas in one catalog (RBAC isolated)
AI / ML
MLflow · Model Serving · Genie AI ✓

## Slide 4
Cost Analysis & ROI
Chart: 
| Licensing | Compute | Storage | Support
Dataiku DSS (Current) | 30900 | 0 | 0 | 0
Databricks (Proposed) | 0 | 4009 | 28 | 200
DATABRICKS BREAKDOWN
Prod App compute
~$2,964
Dev App compute
~$494
Stage App compute
~$76
Dev notebooks
~$475
Delta Lake storage
~$28
SQL Warehouse
~$200
TOTAL ~$4,237 / year
💰 Annual Savings: ~$26,700 (86% reduction) · All 3 environments included · Break-even within Year 1

## Slide 5
Deployment Model & ADLC Compliance
CI/CD DEPLOYMENT WORKFLOW
1
develop branch
CI/CD → smart-app-dev
Dev self-testing
2
stage branch
CI/CD → smart-app-stage
QA / UAT (qTest)
3
main branch
CI/CD → smart-app-prod
RFC gate required
ADLC COMPLIANCE SATISFIED
✓
QA vs Prod separation
Schema isolation + UC RBAC
✓
Validation before prod
ServiceNow RFC gates CI/CD
✓
Test evidence
qTest (unchanged)
✓
Change tracking
Jira + RFC + Git history
✓
Prod access control
CI/CD service principal only
✓
Audit trail
UC audit log + CI/CD runs
ServiceNow RFC process fully preserved

## Slide 6
AI Integration Roadmap
1
Phase 1 — Post Migration
Flask/FastAPI unchanged on Databricks Apps
Delta Lake replaces Snowflake
Same user experience
Foundation for all future AI
2
Phase 2 — What-If Analysis
MLflow: scenario comparison & tracking
Databricks Workflows: parallel runs
Mosaic AI: instant enrollment predictions
Unity Catalog Feature Store: shared features
3
Phase 3 — Future Enhancements
Genie AI: natural language data queries
Predictive site activation ML model
LLM-assisted scenario generation
Anomaly detection on simulation inputs
All AI capabilities available at no additional infrastructure cost on Databricks

## Slide 7
Migration Plan — 20 Weeks
1
Foundation
Wks 1–4
Provision Unity Catalog + RBAC
CI/CD pipeline setup (DAB)
ADLC compliance sign-off
2
Data Migration
Wks 5–8
Migrate 14 Snowflake tables
Delta Lake schema validation
DB connector update
3
App Migration
Wks 5–12
Deploy Flask app on Databricks
Multi-env config adaptation
Dev testing iteration
4
QA & Validation
Wks 13–16
Full QA/UAT in stage
qTest evidence capture
ServiceNow RFC raised
5
Go-Live
Wks 17–20
RFC approval → prod deploy
2-week parallel run
DSS decommission

## Slide 8
We Recommend
Proceed with
the Migration
💰 86% cost saving — $26.7K/yr
🔗 Strategic platform alignment (GPDIP)
⚙ Operational independence via CI/CD
🤖 AI-ready without extra infrastructure
IMMEDIATE NEXT STEPS
1. Confirm workspace with Digital/Platform team
2. Identify migration lead & confirm team availability
3. 1-week PoC: deploy Flask app as Databricks App

## Slide 9
?
CLIENT QUESTIONS — DAN
Responses to
Dan's Queries
Feasibility check completed · Migration app built with live UI, APIs & Delta Lake tables
Q1 — Risks & Cons to consider
Q2 — UI, UX & performance impact
Q3 — Feature work during migration
SMArT Platform Migration · Response to Dan's Review

## Slide 10
Q1
Risks & Cons to Consider
We are transparent about trade-offs. These are manageable risks — none are blockers, and all have defined mitigations.
LOW RISK
Short-term team upskilling
Team needs to learn Databricks Apps, DAB & CI/CD patterns. Mitigated by feasibility spike already completed — team is hands-on from day one.
LOW RISK
No physical environment isolation
Logical schema separation replaces physical DSS instances. UC RBAC enforces access boundaries; reviewed and accepted by compliance approach.
MED RISK
Migration window carries delivery risk
20-week project introduces schedule risk. Phased delivery with parallel-run period and rollback path (DSS stays live until RFC sign-off) contains impact.
LOW RISK
Usage-based cost variability
Unlike fixed DSS licenses, Databricks costs scale with usage. Auto-shutdown on dev/stage and cost dashboards keep this well within the $4.2K estimate.
LOW RISK
Data migration validation effort
14 Snowflake tables must be migrated and verified. Row-count and schema validation scripts are part of Phase 2; feasibility run confirms process works.
MED RISK
Dependency on Digital/Platform team
Workspace assignment (ATP GPD Expl) needs Digital team confirmation. Already flagged as first action item; planning can proceed in parallel under Option A.
✓ Overall assessment: No identified cons are blockers. Risk profile is LOW–MEDIUM. Feasibility PoC de-risks the highest-uncertainty items.

## Slide 11
Q2
UI, End-User Experience & Performance
✅ Feasibility proven: Migration app built with exact UI, live backend APIs & Delta Lake tables — user experience validated end-to-end.
🖥 UI & Frontend
Redesign needed?
None
Identical Flask/FastAPI frontend deployed as Databricks App — same screens, same navigation, same URLs.
Functionality loss?
None
All features confirmed working in the PoC migration. No capability is removed or degraded.
Look & feel change?
None
Databricks App is a thin hosting wrapper — users will not see any platform change.
⚡ Performance
Calculation speed
Same / Faster
Same Python simulation engine. Databricks serverless compute removes DSS scheduler overhead.
Page load times
No change
API layer is unchanged. Delta Lake SQL connector benchmarks comparably to Snowflake at this data volume (<100 GB).
Peak load (50 users)
Handled
Medium instance (2 vCPU / 6 GB) sized for <100 concurrent. Scale-up to Large available on demand.
👤 User Impact
Training required?
None
End users interact with the same web application. No Databricks knowledge needed by users.
URL / access change?
New URL
Each environment gets a dedicated Databricks App URL. A bookmark update is the only visible change for users.
Downtime at cutover?
Zero planned
2-week parallel run means DSS and Databricks run simultaneously. Cutover is a DNS/redirect flip.

## Slide 12
Q3
Feature Work During the Migration
✅ Short answer: Feature work does NOT need to be paused. Migration and new features can run in parallel.
HOW THIS WORKS IN PRACTICE
MIGRATION
TRACK
Foundation
Wks 1–4
Data
Wks 5–8
App Migration
Wks 5–12
QA / UAT
Wks 13–16
Go-Live
Wks 17–20
FEATURE
TRACK
Bug fixes &
maintenance
New Feature A
(on DSS)
New Feature B
(on DSS)
Feature C → DBX
(new home)
Cutover
THE GUARDRAILS
1
New features built on DSS as normal
During migration, feature development continues on the current DSS platform. No change to today's dev/QA/release workflow for new features.
2
Migration team is a dedicated workstream
Migration is run as a parallel project track — it does not consume the full team. Feature sprints and migration sprints are planned independently.
3
Features completed before cutover ship on DSS; after cutover on Databricks
Any feature in flight at Go-Live week is evaluated: if complete → ship on DSS, if not → brief hold during 2-week parallel run, then deliver on Databricks.

## Slide 13
✦
Genie AI — Natural Language Querying for SMArT
Users ask plain-English questions against SMArT's Delta Lake tables — no SQL, no dashboards. Three implementation paths, increasing in capability.
1
✅ READY NOW
Genie Space
Standalone — zero code changes
Create a Genie Space in Databricks pointing to smart_poc.smart.* Delta tables. Users ask questions directly in the Databricks workspace UI.
EXAMPLE QUESTIONS
💬 "Which country has the highest P90 days?"
💬 "Show activation timelines for Argentina"
💬 "Avg site activation rate across countries?"
⚡ Separate UI — users leave the SMArT app
2
⚠ REQUIRES WORK
Embed Genie in App
Chat widget inside SMArT webapp
Add a chat widget in the React frontend. Flask backend proxies calls to the Genie Conversation API. Results rendered inline in the app.
EXAMPLE QUESTIONS
💬 Genie Conversation API
💬 Flask → Genie API proxy
💬 SQL results inline in app UI
⚡ Cannot answer questions about live in-memory API results
3
🔄 BEST OF BOTH
Write Results → Genie Queries
Most powerful approach
Analysis results are saved back to Delta tables (site_activation_details_results etc.). Genie queries saved results — combines live app + historical analysis.
EXAMPLE QUESTIONS
💬 "Show all plans created this week"
💬 "Compare P90 dates across my last 3 runs"
💬 "Which analysis had the fastest activation?"
⚡ Requires result-persistence logic in app layer

## Slide 14
✦
Genie — Recommended Path & Architecture
★ RECOMMENDED FOR PoC DEMO — OPTION 1
1
Open ATP GPD Expl workspace → Genie (sidebar)
2
Create a Genie Space → connect to smart_poc.smart.*
3
Point at smart_category_activation_timelines table
4
Demo alongside app — zero code changes required
✓ CAN answer
✓ Questions about Delta Lake tables
✓ Raw data, saved plans, timelines
✓ Historical result comparisons (Opt 3)
✗ CANNOT answer
✗ Live API/in-memory computation results
✗ Runtime simulation state
✗ Unless Option 3 (write back) is implemented
OPTION 3 — TARGET ARCHITECTURE (Best of Both)
SMArT Web App
React + Flask/FastAPI
Flask Backend
Proxy → Genie Conversation API
Delta Lake Tables
smart_poc.smart.* + results tables
Genie Space
Natural language → SQL → Delta Lake
Result write-back:
site_activation_details_results · summary_results → queryable by Genie

## Slide 15
$
DETAILED COST ANALYSIS
Databricks Pricing
& Cost Strategies
AWS Premium Tier · All 3 Environments · Pay-as-you-go → Committed pricing
Per-environment breakdown
3 cost scenarios
Optimization strategies
Current stack comparison
SMArT Platform Migration · June 2026

## Slide 16
DBU Rates & Per-Environment Cost Breakdown
DBU RATES — AWS Premium Tier
Databricks App (Medium)
$0.275/hr
SQL Serverless Warehouse
$1.10/hr active
1-yr commit discount
25–45% saving
3-yr commit discount
40–55% saving
🛠 DEV
App (10 hrs/day × 22 days)
$60–$80
SQL Warehouse (~2 hrs/day)
$48–$60
Delta Lake Storage (~10 GB)
$2–$5
Unity Catalog
Included
TOTAL ~$110–$145/mo
🧪 STAGE
App (8 hrs/day × 22 days)
$48–$65
SQL Warehouse (~1 hr/day)
$24–$30
Delta Lake Storage (~10 GB)
$2–$5
Unity Catalog
Included
TOTAL ~$75–$100/mo
🚀 PROD
App (24/7 always-on)
$200–$270
SQL Warehouse (~4 hrs/day)
$96–$120
Delta Lake Storage (50–100 GB)
$10–$25
Unity Catalog
Included
TOTAL ~$305–$415/mo
ℹ App size: Medium (0.5 DBU/hr) · DBU rate: $0.55 pay-as-you-go · Region: AWS us-east-1 · Unity Catalog included at Premium tier

## Slide 18
Cost Optimization Strategies
1
40–60% on Dev/Stage
Stop Dev/Stage outside business hours
Auto-shutdown after 30-min idle. Dev/Stage only run ~10 hrs/day instead of 24/7. Biggest single lever for non-prod environments.
2
25–45% across all envs
Committed DBU pricing (1yr or 3yr)
1-year commit: ~$0.40–0.50/DBU vs $0.55 pay-as-you-go. 3-year commit: ~$0.30–0.40/DBU. Significant reduction once usage is proven stable.
3
50% on App compute
Small app size instead of Medium
Downsize from Medium (0.5 DBU/hr) to Small (0.25 DBU/hr) for Dev/Stage. Halves App compute cost if performance is sufficient for non-prod workloads.
4
Pay only for queries
Serverless SQL auto-suspend
Default Serverless Warehouse behaviour — billing stops immediately when idle. No minimum charge. Combine with query result caching to reduce active hours.
5
Reduce workspace overhead
Dev/Stage share a single workspace
Schema-based isolation within one workspace eliminates duplicate workspace overhead. Unity Catalog RBAC enforces access control between schemas.
Optimised (off-hours + 1yr commit): ~$350/mo (~$4,200/yr) | Off-hours + 3yr commit: ~$280/mo (~$3,360/yr)

## Slide 19
Stack Comparison: Current vs Databricks
CURRENT — Dataiku + Snowflake
PROPOSED — Databricks
Platform License
Dataiku license (significant fixed cost)
→
Included in DBU consumption
Compute Model
Dataiku infrastructure (fixed)
→
Serverless — pay-per-use only
Database Cost
Snowflake — separate license + compute
→
Delta Lake — S3 storage at $0.023/GB/mo
App Hosting
Dataiku webapp
→
Databricks Apps (0.5 DBU/hr)
Data Governance
Manual / limited
→
Unity Catalog — included with Premium
CI/CD
Custom setup required
→
Databricks Asset Bundles (DABs) native
Dev/Stage Cost
Fixed (same as prod license cost)
→
Usage-based — auto-shutdown saves 40–60%
Annual Total (est.)
$30,900/yr
→
$4,200–$5,880/yr (optimised–conservative)

## Slide 20
Recommended Cost Strategy & Savings Roadmap
Day 1
Go-Live
Pay-as-you-go
+ Auto-shutdown
~$350/mo
~$4,200/yr
86% vs DSS
Medium app (0.5 DBU/hr) all envs
Dev/Stage off-hours auto-shutdown
Serverless SQL, no idle cost
Unity Catalog included
Year 1
Review
1-Year
Commit (CUD)
~$230/mo
~$2,760/yr
91% vs DSS
Apply 1yr commit after usage proven
Rate drops to ~$0.40–0.50/DBU
Review app sizing (Small vs Medium)
~25–45% further reduction
Year 2+
Optimised
Small App Size
+ 1yr CUD
~$180/mo
~$2,160/yr
93% vs DSS
Downsize Dev/Stage to Small (0.25 DBU)
Prod stays Medium if load requires
Further 50% App compute reduction
Dev/Stage share single workspace
Year 3+
Full Optimised
3-Year
Commit (CUD)
~$140/mo
~$1,680/yr
95% vs DSS
3yr commit: ~$0.30–0.40/DBU
Lowest possible unit cost
Full AI stack (Genie, MLflow) included
Cost well below any alternative